WAREHOUSE CONSTRUCTION PROJECT

COST ANALYSIS REPORT

Prepared by: Allwell Dediribe

Date: August 12, 2026

Tool: Microsoft Excel (PivotTables, PivotCharts, Slicers, Dashboard)

# Executive Summary

A ₦100,000,000 warehouse construction budget had ₦70,000,000 already spent by the block work stage, the earliest phase of the build. That left ₦30,000,000 in the budget, against a completion cost estimated at ₦50,000,000. The project carries a funding gap of ₦20,000,000 and is flagged At Risk. This report breaks down where the money went, why the gap opened up, and what management can do about it before the next phase starts.

# Business Problem

The construction company raised a concern: ₦70,000,000 of a ₦100,000,000 budget was gone, and the project had only reached block work, the second phase of a multi-phase build. Management needed a clear answer to one question: could the remaining ₦30,000,000 finish the project, and if not, why.

# Project Objectives

- Compare actual project spending against the approved budget.

- Identify which phases and activities put the most pressure on the budget.

- Break down costs by material, supplier, and labour activity.

- Test whether the remaining budget could complete the project.

- Turn the findings into recommendations management can act on.

# Dataset Description

The dataset tracked project phases, activities, materials, suppliers, quantities, and costs. It included planned budget, actual cost, and variance for every activity, plus separate columns for labour, equipment, and transportation expenses. Each record could be traced back to a phase, a month, and a supplier, which made it possible to filter the dashboard three ways: by phase, by month, and by supplier.

# Data Cleaning and Preparation

- Checked all cost and quantity fields for correct number formatting before building any PivotTable.

- Standardized phase, activity, and supplier names so the same entry did not appear under two different spellings.

- Confirmed variance figures (planned budget minus actual cost) calculated correctly for every row.

- Found that the month field was stored as text rather than a date, which caused the expenditure trend chart to sort months alphabetically instead of by calendar order. This is flagged here rather than hidden, since it affects how the monthly trend should be read.

# Tools Used

Microsoft Excel handled the full workflow.

PivotTables aggregated cost by phase, material, supplier, and activity.

PivotCharts turned those aggregates into visuals.

Slicers for phase, month, and supplier made the dashboard interactive.

KPI cards on the dashboard surfaced budget, spend, remaining funds, and funding gap at a glance.

# Analysis Methodology

- Defined the business problem: an unclear gap between spend and physical progress.

- Cleaned and standardized the dataset.

- Built PivotTables to break down cost by phase, material, supplier, and labour activity.

- Charted the monthly expenditure trend to see how spending moved over time.

- Assembled the findings into one dashboard with KPI cards and six supporting charts.

- Converted the findings into recommendations for management.

# Dashboard Overview

The dashboard leads with five KPI cards, then six charts that break the numbers down further.

| TOTAL BUDGET ₦100,000,000 | SPENT TO DATE ₦70,000,000 70% of budget | REMAINING BUDGET ₦30,000,000 30% of budget | FUNDING GAP ₦20,000,000 projected |
| --- | --- | --- | --- |

The six supporting charts cover phase cost versus budget, the monthly expenditure trend, cost per material, cost by supplier, labor cost per activity, and a side-by-side of remaining budget against remaining completion cost.

# Key Findings

## 1. Block work is where the budget broke

Block work carries the highest cost of any phase completed so far and shows the largest positive variance against its planned budget. Foundation work is the second-largest cost driver. Together, these two early phases explain most of the ₦70,000,000 already spent, before the project has touched finishing, electrical, or plumbing work.

## 2. Materials, not labor, drive the spend

Cost by material, filtered to the block work phase:

| Material | Cost (₦) | Share |
| --- | --- | --- |
| Blocks | 38,000,000 | 54.3% |
| Cement | 25,000,000 | 35.7% |
| Gravel | 7,000,000 | 10.0% |
| Roof sheets, electrical, pipes, sand, paint | 0 | 0.0% |

Blocks and cement alone account for 90 percent of material spend at this stage. Materials tied to later phases, roof sheets, pipes, and paint among them, show zero cost, which matches a project still sitting at block work.

## 3. Supplier spend is concentrated in one vendor

| Supplier | Cost (₦) | Share |
| --- | --- | --- |
| Prime Materials Co. | 33,000,000 | 47.1% |
| Mega Builders Depot | 19,000,000 | 27.1% |
| BuildMart Ltd | 16,600,000 | 23.7% |
| Alpha Construction Supply | 1,400,000 | 2.0% |

Prime Materials Co. supplies almost half of everything bought so far. That level of concentration is a procurement risk on its own, separate from the budget overrun: a price change or delivery problem from one supplier now has an outsized effect on the whole project.

## 4. Labor cost is tied to two activities

| Activity | Labour Cost (₦) |
| --- | --- |
| Wall construction | 9,500,000 |
| Concrete foundation | 6,250,000 |
| Land clearing and excavation | 1,750,000 |
| Plastering, roofing, electrical, plumbing, painting | 0 |

Wall construction and concrete foundation together account for ₦15,750,000 in labour cost, almost all of the labor spend recorded to date. This lines up with the material and phase findings: the money has gone into block work and foundation, not into later-stage trades.

## 5. Spending dropped sharply over the project timeline

Monthly expenditure moved from ₦21,600,000 in the highest-spend month down to ₦0 in the most recent one, with a clear step down each period after the first two months. Read together with the phase data, this points to a front-loaded project: the bulk of the budget went out early, in block work and foundation, and spending has since slowed as the project stalled at its current phase.

## 6. The remaining budget cannot finish the project

Remaining budget stands at ₦30,000,000. The estimated cost to complete the remaining phases, finishing, electrical, plumbing, roofing, and painting, comes to ₦50,000,000. That leaves a funding gap of ₦20,000,000. Without a change in scope, budget, or supplier terms, the project cannot finish on the current allocation.

# Recommendations

- Close the ₦20,000,000 funding gap now, either by securing additional funding or by reducing scope on the remaining phases, before committing to any new activity.

- Renegotiate terms with Prime Materials Co., since it holds 47.1 percent of supplier spend. Bring in a second qualified supplier for blocks and cement to reduce that concentration.

- Set a hard cost-to-completion review at the end of every phase, starting immediately, rather than waiting for a scheduled milestone. Block work already shows this control was missing.

- Track block and cement usage against planned quantities on site. These two materials made up 90 percent of spend at this phase, so even a small reduction in waste has a large effect on the total.

- Build a phase-by-phase cost forecast for finishing, electrical, plumbing, roofing, and painting before releasing further funds, using the ₦50,000,000 completion estimate as the starting baseline, not the final figure.

- Fix the month field in the dataset so it stores dates rather than text. This is a small change that prevents the monthly trend chart from sorting out of order.

# Conclusion

The numbers explain what the raw spend figure could not: block work and foundation used most of the budget, two materials and one supplier account for the bulk of that cost, and the ₦30,000,000 left cannot cover the ₦50,000,000 needed to finish. Management now has a specific funding gap, a named supplier risk, and a phase-level breakdown to act on, instead of a single number that only said something was wrong.

# Analyst Reflection

This project sharpened three skills: building a dashboard that answers a business question rather than just displaying data, tracing a high-level number like “70 percent spent” down to the specific phase, material, and supplier behind it, and writing recommendations tied directly to a figure in the data rather than general advice. The clearest lesson was that a budget overrun is not one problem. It is usually several smaller, specific ones, in this case a supplier concentration issue and a materials cost issue, sitting inside one bigger number.

Dashboard

Full dashboard, built in Excel with PivotTables, PivotCharts, and slicers for phase, month, and supplier.