## Construction Cost Data
Date | Project Phase | Activity Name | Material Purchased | Supplier Name | Quantity | Unit Cost (₦) | Material Cost | Total Cost (₦) | Labour Cost (₦) | Equipment Cost (₦) | Transportation Cost (₦) | Other Expenses (₦) | Planned Budget (₦) | Actual Cost (₦) | Variance (₦) | Status | Months
2025-02-11 | Site Preparation | Land clearing and preparation | Gravel | Alpha Construction Supply | 368 | 2092 | 769856 | 1400000 | 350000 | 140000 | 98000 | 42000 | 1000000 | 1400000 | -400000 | Over Budget | Feb
2025-04-08 | Site Preparation | Land clearing and preparation | Gravel | BuildMart Ltd | 457 | 1684 | 769588 | 1400000 | 350000 | 140000 | 98000 | 42000 | 1000000 | 1400000 | -400000 | Over Budget | Apr
2025-03-10 | Site Preparation | Land clearing and preparation | Gravel | Prime Materials Co. | 480 | 1604 | 769920 | 1400000 | 350000 | 140000 | 98000 | 42000 | 1000000 | 1400000 | -400000 | Over Budget | Mar
2025-01-16 | Site Preparation | Land clearing and preparation | Gravel | Prime Materials Co. | 382 | 2015 | 769730 | 1400000 | 350000 | 140000 | 98000 | 42000 | 1000000 | 1400000 | -400000 | Over Budget | Jan
2025-02-26 | Site Preparation | Land clearing and preparation | Gravel | Mega Builders Depot | 107 | 7196 | 769972 | 1400000 | 350000 | 140000 | 98000 | 42000 | 1000000 | 1400000 | -400000 | Over Budget | Feb
2025-02-10 | Foundation | Concrete foundation and reinforcement | Cement | Mega Builders Depot | 494 | 5566 | 2749604 | 5000000 | 1250000 | 500000 | 350000 | 150000 | 4000000 | 5000000 | -1000000 | Over Budget | Feb
2025-01-23 | Foundation | Concrete foundation and reinforcement | Cement | Prime Materials Co. | 328 | 8384 | 2749952 | 5000000 | 1250000 | 500000 | 350000 | 150000 | 4000000 | 5000000 | -1000000 | Over Budget | Jan | 38497503
2025-04-13 | Foundation | Concrete foundation and reinforcement | Cement | Prime Materials Co. | 56 | 49107 | 2749992 | 5000000 | 1250000 | 500000 | 350000 | 150000 | 4000000 | 5000000 | -1000000 | Over Budget | Apr
2025-02-14 | Foundation | Concrete foundation and reinforcement | Cement | Prime Materials Co. | 258 | 10658 | 2749764 | 5000000 | 1250000 | 500000 | 350000 | 150000 | 4000000 | 5000000 | -1000000 | Over Budget | Feb
2025-04-18 | Foundation | Concrete foundation and reinforcement | Cement | Mega Builders Depot | 494 | 5566 | 2749604 | 5000000 | 1250000 | 500000 | 350000 | 150000 | 4000000 | 5000000 | -1000000 | Over Budget | Apr
2025-04-17 | Block Work | Wall construction | Blocks | BuildMart Ltd | 131 | 31908 | 4179948 | 7600000 | 1900000 | 760000 | 532000 | 228000 | 5000000 | 7600000 | -2600000 | Over Budget | Apr
2025-03-30 | Block Work | Wall construction | Blocks | Mega Builders Depot | 121 | 34545 | 4179945 | 7600000 | 1900000 | 760000 | 532000 | 228000 | 5000000 | 7600000 | -2600000 | Over Budget | Mar
2025-01-26 | Block Work | Wall construction | Blocks | BuildMart Ltd | 114 | 36666 | 4179924 | 7600000 | 1900000 | 760000 | 532000 | 228000 | 5000000 | 7600000 | -2600000 | Over Budget | Jan
2025-01-10 | Block Work | Wall construction | Blocks | Prime Materials Co. | 496 | 8427 | 4179792 | 7600000 | 1900000 | 760000 | 532000 | 228000 | 5000000 | 7600000 | -2600000 | Over Budget | Jan
2025-02-06 | Block Work | Wall construction | Blocks | Prime Materials Co. | 446 | 9372 | 4179912 | 7600000 | 1900000 | 760000 | 532000 | 228000 | 5000000 | 7600000 | -2600000 | Over Budget | Feb
2025-01-31 | Roofing | Roof installation | Roof Sheets | Alpha Construction Supply | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Jan
2025-02-04 | Roofing | Roof installation | Roof Sheets | Prime Materials Co. | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Feb
2025-05-10 | Roofing | Roof installation | Roof Sheets | Prime Materials Co. | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | May
2025-02-17 | Roofing | Roof installation | Roof Sheets | BuildMart Ltd | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Feb
2025-03-04 | Roofing | Roof installation | Roof Sheets | Prime Materials Co. | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Mar
2025-02-12 | Finishing | Plastering and finishing works | Sand | BuildMart Ltd | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Feb
2025-02-17 | Finishing | Plastering and finishing works | Sand | BuildMart Ltd | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Feb
2025-04-06 | Finishing | Plastering and finishing works | Sand | Alpha Construction Supply | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Apr
2025-02-18 | Finishing | Plastering and finishing works | Sand | Alpha Construction Supply | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Feb
2025-02-18 | Finishing | Plastering and finishing works | Sand | Mega Builders Depot | 469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 3000000 | Within Budget | Feb
2025-02-19 | Painting | Painting works | Paint | Prime Materials Co. | 406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | Within Budget | Feb
2025-03-11 | Painting | Painting works | Paint | Prime Materials Co. | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | Within Budget | Mar
2025-02-11 | Painting | Painting works | Paint | BuildMart Ltd | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | Within Budget | Feb
2025-02-24 | Painting | Painting works | Paint | Mega Builders Depot | 433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | Within Budget | Feb
2025-03-21 | Painting | Painting works | Paint | Mega Builders Depot | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 1000000 | Within Budget | Mar
2025-02-27 | Electrical Installation | Electrical wiring | Electrical Cables | BuildMart Ltd | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 1400000 | Within Budget | Feb
2025-01-15 | Electrical Installation | Electrical wiring | Electrical Cables | Prime Materials Co. | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 1400000 | Within Budget | Jan
2025-02-04 | Electrical Installation | Electrical wiring | Electrical Cables | BuildMart Ltd | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 1400000 | Within Budget | Feb
2025-02-10 | Electrical Installation | Electrical wiring | Electrical Cables | Mega Builders Depot | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 1400000 | Within Budget | Feb
2025-03-16 | Electrical Installation | Electrical wiring | Electrical Cables | Alpha Construction Supply | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 1400000 | Within Budget | Mar
2025-02-11 | Plumbing | Pipe installation | Pipes | Mega Builders Depot | 318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 1600000 | Within Budget | Feb
2025-03-26 | Plumbing | Pipe installation | Pipes | Alpha Construction Supply | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 1600000 | Within Budget | Mar
2025-02-16 | Plumbing | Pipe installation | Pipes | BuildMart Ltd | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 1600000 | Within Budget | Feb
2025-01-21 | Plumbing | Pipe installation | Pipes | Prime Materials Co. | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 1600000 | Within Budget | Jan
2025-03-16 | Plumbing | Pipe installation | Pipes | Alpha Construction Supply | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600000 | 0 | 1600000 | Within Budget | Mar

## Summary Table
Cost Category | Amount Spent | Precentage Cost | Planned Allocation | Variance (-)
Materials | 38497503 | 55% | 50M | 11.5M
Labour | 17500000 | 25% | 20M | 2.5M
Equipment | 7000000 | 10% | 15M | 8M
Transportation | 4900000 | 7% | 10M | 5.1M
Other Expenses | 2100000 | 3% | 5M | 2.9M
Total | 69997503 | 100% | 100M

## EDA
Activity Name | Sum of Labour Cost (₦) | Supplier Name | Sum of Actual Cost (₦) | % of Actual Cost per Supplier |  | Project Phase | Sum of Labour Cost (₦)
Wall construction | 9500000 | Prime Materials Co. | 33000000 | 47.14% |  | Block Work | 9500000
Concrete foundation and reinforcement | 6250000 | Mega Builders Depot | 19000000 | 27.14% |  | Foundation | 6250000
Land clearing and preparation | 1750000 | BuildMart Ltd | 16600000 | 23.71% |  | Site Preparation | 1750000
Plastering and finishing works | 0 | Alpha Construction Supply | 1400000 | 2% |  | Plumbing | 0
Roof installation | 0 | Grand Total | 70000000 | 100% |  | Roofing | 0
Electrical wiring | 0 |  |  |  |  | Electrical Installation | 0
Pipe installation | 0 | Row Labels | Sum of Actual Cost (₦) | % of Actual Cost per Month |  | Finishing | 0
Painting works | 0 | Jan | 21600000 | 30.86% |  | Painting | 0
Grand Total | 17500000 | Feb | 20400000 | 29.14% |  | Grand Total | 17500000
|  | Apr | 19000000 | 27.14%
Material Purchased | Total Cost per Material (₦) | Mar | 9000000 | 12.86% |  | Labour Cost Percentage | 25
Paint | 0 | May | 0 | 0%
Sand | 0 | Grand Total | 70000000 | 100% |  | #VALUE!
Pipes | 0
Electrical Cables | 0 | Project Phase | Total Cost per Activity (₦) | Sum of Planned Budget (₦) | Sum of Variance (₦)
Roof Sheets | 0 | Block Work | 38000000 | 25000000 | -13000000
Gravel | 7000000 | Foundation | 25000000 | 20000000 | -5000000
Cement | 25000000 | Site Preparation | 7000000 | 5000000 | -2000000
Blocks | 38000000 | Plumbing | 0 | 8000000 | 8000000
Grand Total | 70000000 | Roofing | 0 | 15000000 | 15000000
|  | Electrical Installation | 0 | 7000000 | 7000000 | Category | Amount
Activity Name | Total Cost per Activity (₦) | Finishing | 0 | 15000000 | 15000000 | Remaining Budget Available | 30000000
Wall construction | 38000000 | Painting | 0 | 5000000 | 5000000 | Remaining Completion Cost | 50000000
Concrete foundation and reinforcement | 25000000 | Grand Total | 70000000 | 100000000 | 30000000
Land clearing and preparation | 7000000 | [5 empty] | 20000000
Plastering and finishing works | 0
Roof installation | 0
Electrical wiring | 0
Pipe installation | 0
Painting works | 0
Grand Total | 70000000

## Dashboard
WAREHOUSE CONSTRUCTION PROJECT COST ANALYSIS
Project Financial Performance Overview
TOTAL PROJECT BUDGET
₦100,000,000
PROJECTED FUNDING GAP
₦20,000,000
AMOUNT SPENT TO DATE
₦70,000,000
70% of Budget
REMAINING BUDGET
₦30,000,000
30% of Budget
PROJECT STATUS
At Risk
Budget Overrun
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Sheet1
Key Insights
1. Block work consumed the highest amount of project funds, with actual spending exceeding its planned allocation. This indicates that the block work stage is the major driver of the project's early budget depletion.
Recommendation:
Review block work expenses, especially material quantities, supplier pricing, and labour requirements.
Implement stricter cost monitoring before approving future construction stages.
2. Materials represent the largest portion of total project expenditure, making them the primary area requiring cost control. High material consumption contributed significantly to the rapid reduction of the available budget.
Recommendation:
Negotiate better prices with suppliers.
Compare multiple suppliers before major purchases.
Consider bulk purchasing agreements to reduce material costs.
Track material usage against project requirements to reduce waste.
3. The project has already spent ₦70M out of the ₦100M total budget while only reaching the block work stage, leaving ₦30M for the remaining construction phases.
Recommendation:
Introduce milestone-based budget reviews before moving to each construction phase.
Require management approval for high-value expenses.
Conduct regular cost-to-completion forecasts.
4. The estimated cost of completing the remaining stages (roofing, finishing, painting, electrical installation, and plumbing) exceeds the available ₦30M balance, creating a projected funding gap.
Recommendation:
Secure additional funding before continuing construction.
Prioritize essential remaining activities.
Reassess the project scope and identify areas where costs can be reduced.
5. Foundation and block work stages consumed a significant percentage of the total budget, suggesting that early project activities were more expensive than initially planned.
Recommendation:
Improve initial project cost estimation.
Perform detailed feasibility studies before construction begins.
Use historical project data to create more accurate future budgets.
Monitor project performance using cost variance tracking.